## Feasibility
Feasibility Study – Car Service Booking with Status Updates
Feasibility Summary
Type | Current Situation / Considerations | Proposed Solution / Benefits | Feasibility Result
Technical | Bookings by phone and paper; no tracking of car status. | Web application with a database and SMS / e-mail notifications. | Technically feasible
Operational | Staff spend a lot of time on calls; double bookings happen. | Online booking and status updates; fewer calls and errors. | Operationally feasible
Economic | Cost of development, hosting, training and maintenance. | Saves staff time and paper, increases bookings (see table below). | Cost-effective
Legal | System stores customers' personal data. | Login with roles, protect the data, follow data protection law. | Legally feasible
Schedule | Manual work cannot be improved quickly. | About 3–5 months to build and test the system. | Achievable timeline
Cost–Benefit Analysis – Car Service Booking with Status Updates
Category | Description | Estimated Cost (EGP) | Benefits | Estimated Value (EGP per year)
Software | Development, UI design and testing (one-time) | 53000 | Online booking with free time slots, 24/7; brings extra bookings. | 28800
Hardware | Hosting setup and 3 tablets for technicians (one-time) | 15000 | Fast status updates from the workshop; reminders reduce no-shows. | 36000
Training | Staff training sessions (one-time) | 4000 | Smooth transition, staff use the system correctly. | -
Maintenance | Hosting, SMS fees, updates and bug fixes (yearly) | 21760 | Keeps the system reliable and secure. | -
Administration | Current manual system (notebooks, paper forms, phone calls) | - | Less paper and less staff time spent on calls. | 30960
User Experience | Customers call to ask about their car | - | Customers follow car status online; higher satisfaction. | Intangible but high value
Summary
Total one-time costs |  | 72000
Total yearly costs |  | 21760
Total annual benefits |  | 95760
Net benefit per year |  | 74000
Payback period (months) |  | 11.6757
ROI after 3 years |  | 208.3%
Conclusion: The Car Service Booking system is economically feasible, with clear cost savings and long-term value.
Note: all amounts are team estimates.